## Gantt
Track | Task | Start (week) | End (week) | Duration (weeks) | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9
2026-10-08
[5 empty] | Project requirements |  | Report |  | Milestone I |  | Report |  | Deadline
Organization | Project requirements | 1 | 1
Game engine | Core: deterministic step, shared config (JSON), movement, collisions | 2 | 2
Game engine | Browser client (hitboxes), headless mode, replay | 2 | 3
Levels | Level format (JSON) + handmade test levels | 2 | 3
Game engine | Blocks, coins, flagpole, basic enemies (Goomba, Koopa) | 3 | 4
Game engine | Pipes + sub-areas | 4 | 5
Game engine | SMB1 power-ups: mushroom, fire flower, star | 4 | 5
Bot | Training environment + Python server link | 4 | 4
Bot | Neuroevolution bot | 4 | 5
Game engine | SMB3 power-ups: leaf, tanooki, frog, hammer, stopwatch | 5 | 7
Game engine | Remaining enemies (list not final) | 6 | 7
Levels | Segment import from original levels | 5 | 6
Levels | Segment-based procedural generator | 6 | 7
Levels | Datasets: tiers, train/val/test, level metrics | 7 | 7
Organization | Human time measurement | 7 | 8
Bot | RL bot | 6 | 8
Bot | Evolution vs RL: evaluation on the test set | 8 | 9
Graphics | Graphics and sound (original sprites) | 7 | 9
Game engine | Performance optimization | 9 | 9
Organization | Final report | 9 | 9
Legend
Organization | Blue text = editable cells
Game engine
Levels
Bot
Graphics
Note on F5: Date of the first schedule deadline (08.10.2026).