## Gantt
Track | Task | Start (week) | End (week) | Duration (weeks) | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9
[5 empty] | 2026-10-08 | 2026-10-15 | 2026-10-22 | 2026-10-29 | 2026-11-05 | 2026-11-12 | 2026-11-19 | 2026-11-26 | 2026-12-03
[5 empty] | Project requirements |  | Report |  | Milestone I |  | Report |  | Deadline
Organization | Project requirements | 1 | 1 | 1
Game engine | Basics: movement, jump, collisions, obstacles, restart | 2 | 3 | 2
Game engine | Deterministic physics, headless mode | 2 | 3 | 2
Levels | Level format + 2–3 handmade levels | 2 | 3 | 2
Graphics | Graphic assets | 2 | 8 | 7
Game engine | Dash, climbing, stamina, buttons, checkpoints, coins | 4 | 5 | 2
Bot | Bot environment interface | 4 | 4 | 1
Bot | Bot v1 | 4 | 5 | 2
Levels | Procedural generator | 6 | 7 | 2
Organization | Human completion time measurement | 6 | 6 | 1
Levels | Test set of 10 levels | 7 | 7 | 1
Bot | Bot v2 | 8 | 8 | 1
Bot | Evaluation on 10 test levels | 8 | 9 | 2
Game engine | Performance optimization | 9 | 9 | 1
Organization | Final report | 9 | 9 | 1
Legend
Organization
Game engine | Plan drafted with Claude, 07.10.2026
Levels
Bot
Graphics